## Read me
QA checklist for Issue Report #16
About
Date / baseline | 2026-10-24. HEAD = 5abd155 ('F9, F14a, N62, N27'): Codex's TASK-N27 and TASK-F9_F14a_N62, already committed by you.
Sources | Issue Report #16 §1 (Docs/AI/Reports/2026-10-24_IssueReport-16.md), §9 of the two specs (Docs/AI/Tasks/), and Codex's report 2026-10-24_F9_F14a_N62_Implementation.md §6. TASK-N27 has no Codex report (its session was interrupted); its evidence is in build/n27-verification/. | Owner | 2026-10-28
Code review (Claude) | I checked both diffs line by line against the specs: they match. • N27, Codex's harness: 'Invalid mane material index.' 4 times before, 0 after; mane height / body height 0.544 (target 0.54 ± 0.05); a respawn keeps the colour; 1,000 picks cover all five colours. I looked at its renders: the mane sits right. • F9 / F14a / N62: fades measured 0.77 s in (with a first-use frame) and 0.62 s out; the six boxes checked at 2 sizes × 3 languages; the UI6 sweep has its 199 old diagnostics and no new one; the release build succeeded. • I didn't run Unity myself. No harness can play a real remote client: this checklist is the real test. | Owner | 2026-10-28
Why | When this checklist passes, N27, N62, F9 and F14a close, and Codex can start the next two tasks (the counters F15 / F16 with N64, and N63 with your new mane palette). | Owner | 2026-10-28
Who runs it | The developer: A–D and H in two Unity Editors (ParrelSync), E in one Editor (optional), G with a new Windows build plus an Editor. | Owner | 2026-10-28
Order | A → B → C → D in two or three matches (they can share matches). E (network off) whenever convenient. Then G (build) and H at the end. | Owner | 2026-10-28 | White, brown
How to report | 1. Set Status on every row of the Checklist sheet. The Summary sheet updates by itself. 2. For every Fail, paste the Console text (error plus stack trace) into 'Console output / notes'. For a visual Fail, save a screenshot and write its file name there. 3. A2.1 and A4.1: write the mane colours you saw. 4. If you run rows on your second machine, write 'PC 2' in Tested by. 5. New problems you notice: add them at the bottom of the Known issues sheet ('Found during the checks'). I read every sheet. 6. Please type only in the yellow cells: last time the clone-start text landed in C1.4's Group cell (harmless, but the Summary counted C1 with one row less). 7. Tell Claude when you're done. | Owner | 2026-10-28
|  | Owner | 2026-10-28
Legend
Cells to fill in | Only the yellow cells on the Checklist sheet: Status, Tested by, Date, Console output / notes. Everything else is reference text or formulas. | Owner | 2026-10-28
Pass | Every expected result in the row was seen. | Owner | 2026-10-28
Fail | At least one expected result wasn't seen, or a new error appeared. Add the Console text or a screenshot name. (Typing False also counts as Fail.) | Owner | 2026-10-28
Blocked | The row couldn't be run (e.g. an earlier failure). Say why in the notes. | Owner | 2026-10-28
Not run | Skipped on purpose. Fine for optional rows; for a required row it keeps the group open. | Owner | 2026-10-28
N/A | Doesn't apply in this setup. Counts like a Pass for the group result. | Owner | 2026-10-28
Optional = Yes | Optional rows don't hold back a group's Pass result.
Grey text | In a group's second and later rows, Check / Covers / Task / Run as / Size repeat the first row so that filtering works. | Owner | 2026-10-28
|  | Owner | 2026-10-28
Preparation |  | Owner | 2026-10-28
1. The clone with its own log | Start the clone from PowerShell, so that it writes its own log: & 'C:\Program Files\Unity\Hub\Editor\6000.3.13f1\Editor\Unity.exe' -projectPath 'C:\Lesson\FallenStar-Spellcasters_clone_1' -logFile 'C:\Lesson\clone-editor.log' Last round the clone ran without it at least once: its lines went into the shared Editor.log and replaced the main Editor's, so I couldn't read the host side of A4. | Owner | 2026-10-28
2. Console | In both Editors, open the Console: Collapse off, Clear on Play on.
3. Clean start | Both Editors in English unless a row says otherwise. git status may show the font asset as modified: that's fine during the checks (see 'Before you commit'). | Owner | 2026-10-28
4. Start a match | Log in and go to the Lobby in both windows. The main Editor presses Create Lobby: from now on it's the host window. The clone presses Find Lobby, selects the lobby and presses Join: it's the client window. The host presses Start game. | Owner | 2026-10-28
5. Game view | 1920×1080 in both Editors unless a row names another size (C1.2 uses 1280×720). | Owner | 2026-10-28
|  | Owner | 2026-10-28
Useful facts
Table sides | Both windows look at the table from the same camera. The HOST's cards, pony and blocks are on the LEFT (red side); the CLIENT's on the RIGHT (blue side). | Owner | 2026-10-28
New this round | • Each pony has a mane. The server picks a different colour for each player before the first spawn and keeps it until the match ends. • The big card fades in (0.7 s) and out (0.6 s). The two times are fields on CardPreviewController (PlayerSessionPrefab). • Six HUD texts have a dark box behind them: HP, Life, Mana, Opponent mana, the announcer and the hint line. • Send during the opponent's turn now says 'It's your opponent's turn.' | Owner | 2026-10-28
Casting | In your Player action: left-click the played card in the BOTTOM HUD ROW → click the target on the table → Confirm → Send. Self cards (Healing Hooves, Clarity) choose their target automatically. | Owner | 2026-10-28
Phases (en) | Line 1 of the announcer: 'Round preparation' (5 s), 'Drawing cards' (about 3 s), 'Card Selection' (60 s), 'Player action' (60 s per player), 'Waiting for respawn' (30 s).
Controls | Hand cards: left-click = play, right-click = discard. Confirm Turn confirms the selection in Card Selection, ends your Player action, and confirms the respawn block in Waiting for respawn. W/A/S/D = one step (own Player action). Space = −10 HP to yourself (own Player action; Editor and development builds only). | Owner | 2026-10-28
Kill a pony at any moment | In the HOST window's Scene view, select the pony (PonyBase(Clone)) and drag it sideways off its platform, or add about 20 to its Transform Position X or Z. It falls into the lava and dies. Host window only: the lava check runs on the server. | Owner | 2026-10-28
Switch language | Main menu → Settings (remembered). In the lobby or during a match: Window → Asset Management → Localization Scene Controls → Active Locale. | Owner | 2026-10-28
Player build | Build to C:\Lesson\Spellcasters.Build\ (row G1.1). Its log: %USERPROFILE%\AppData\LocalLow\DefaultCompany\FallenStar-Spellcasters\Player.log (moved to Player-prev.log at each start). Make a NEW build: the pony prefab changed, so an older build can't play against today's Editor.
|  | Owner | 2026-10-28
Changes from the last checklist (2026-10-24, #15) |  | Owner | 2026-10-28
IDs | New numbering: A–H here aren't last round's A–H.
Last round's results | 34 Pass, 4 N/A, 4 optional rows not run, no Fail. N59, N61, N36, F1, F4, F6 and UI7 are closed (report #16).
Your notes | • A4.1 'lobby not found': a lobby refresh that finishes after your own Disconnect. Now N63, fixed by the next task. • B 'can't be run': the clone's log shows all three offline attempts did run (two Find Lobby timeouts, a Create Lobby timeout, a failed sign-in). The message comes only after the 10 s timeout. Section E repeats them with a 15 s wait (optional).
Before you commit
1. Language | Set both Editors back to English.
2. The font | With both Editors closed: git restore "Assets/Fonts/MPLUSRounded1c-Medium SDF.asset"
3. The pony prefab | git status must not show PonyBase.prefab (A1.1 only looks at it). If it does: git restore Assets/Prefab/BoardPrefab/PonyBase.prefab
4. Nothing else | This round has no temporary code change. Only the docs from report #16 should be new or deleted.

## Checklist
QA checklist: N27 (mane), F9 (fade), F14a (dark boxes) and N62 (Issue Report #16)
Baseline 5abd155 ('F9, F14a, N62, N27', 2026-10-24): Codex's two tasks, already committed. Fill in only the yellow cells. Optional rows don't hold back a group.
ID | Group | Check | Covers | Task | Run as | Size | Steps | Expected result | Optional | Status | Tested by | Date | Console output / notes
A. The mane (N27). Two Editors; main = host, clone = client (Read me → Preparation).
A1.1 | A1 | The mane sits on the head | N27 | N27 | Host | — | Open Assets/Prefab/BoardPrefab/PonyBase.prefab (double-click). Look at the pony from the front, the side and ¾. | The mane sits on the head and neck from every angle, the forelock between the ears. Nothing purple. Close the prefab without saving if Unity asks. |  | Pass | Owner | 2026-10-28
A2.1 | A2 | Two different colours, the same on both peers | N27 | N27 | Host | 1920×1080 | Start a match (Read me → Preparation 4). In the HOST window look at both ponies. Write the two mane colours in the notes (e.g. 'left gold, right black'). | Both ponies have a mane. The two colours differ and are from: white, black, brown, gold, pink. |  | Pass | Owner | 2026-10-28
A2.2 | A2 | Two different colours, the same on both peers | N27 | N27 | Client | 1920×1080 | Same match, CLIENT window. | The same colour on the same pony as in the host window (host = left / red, client = right / blue). |  | Pass | Owner | 2026-10-28
A3.1 | A3 | A respawn keeps the colour | N27 | N27 | Both | 1920×1080 | Kill a pony (Read me → Kill a pony, host window). Confirm the respawn block. | The respawned pony has the same mane colour as before, in both windows. |  | Pass | Owner | 2026-10-28
A4.1 | A4 | A new match picks again | N27 | N27 | Both | 1920×1080 | End the match (Leave match → Leave is fastest). Both: Result → Main menu → Lobby → a new match. | The colours are picked again (they may stay the same by chance). The two ponies still differ. Write the colours. |  | Pass | Owner | 2026-10-28 | White, brown
A4.2 | A4 | A new match picks again | N27 | N27 | Both | 1920×1080 | Repeat A4.1 two more times. | Each time the two colours differ. Over the three matches you probably see at least three different colours. | Yes | Pass | Owner | 2026-10-28
A5.1 | A5 | Selection still works | N27 | N27 | Both | 1920×1080 | In your own Player action, click a pony on the table (as a target), then click the empty ground. | The clicked pony turns white, body AND mane. Afterwards both get their colours back (body = team colour, mane = its colour). |  | Pass | Owner | 2026-10-28
B. The big-card fade (F9). Two Editors, Card Selection unless a row says otherwise.
B1.1 | B1 | Fade in and out | F9 | F9_F14a_N62 | Both | 1920×1080 | Hover a card in your hand row (bottom of the screen) for 2 s, then move the pointer away. | The big card appears softly (about 0.7 s) and disappears softly (about 0.6 s). |  | Pass | Owner | 2026-10-28
B1.2 | B1 | Fade in and out | F9 | F9_F14a_N62 | Both | 1920×1080 | Sweep the pointer quickly back and forth across all your hand cards, then away from the hand. | The big card follows the pointer with short cross-fades. No flicker, no stuck card. Shortly after you leave, nothing stays on screen. |  | Pass | Owner | 2026-10-28
B1.3 | B1 | Fade in and out | F9 | F9_F14a_N62 | Both | 1920×1080 | Click a card on the TABLE (left or right side) twice, then click empty ground. | The second click keeps the same big card (no flash). The ground click fades it out. |  | Pass | Owner | 2026-10-28
B1.4 | B1 | Fade in and out | F9 | F9_F14a_N62 | Both | 1920×1080 | In your own Player action: hover a card in the bottom row, move away, and while its big card is still fading, click a target on the table. | The table click works as usual (the fading card doesn't block it). |  | Pass | Owner | 2026-10-28
B2.1 | B2 | The durations are editable | F9 | F9_F14a_N62 | Host | 1920×1080 | In Play Mode, in the Hierarchy select each PlayerSessionPrefab(Clone) → CardPreviewController and set Fade In Duration 2 and Fade Out Duration 2. Hover a card and leave. | Both fades now take about 2 s. (Play Mode changes are undone when you stop: nothing to restore.) | Yes | Pass | Owner | 2026-10-28
B3.1 | B3 | No fade after leaving | F9 | F9_F14a_N62 | Client | 1920×1080 | With a big card on screen, press Leave match → Leave. | The big card is gone at once; nothing fades over the Result screen. | Yes | Pass | Owner | 2026-10-28
C. Dark boxes behind the HUD texts (F14a). Two Editors.
C1.1 | C1 | Six texts have a dark box | F14a | F9_F14a_N62 | Both | 1920×1080 | en, 1920×1080, during a Player action with a hint shown (e.g. press Confirm with no card picked). | Dark boxes behind: HP, Life, Mana, Opponent mana, the announcer (both lines) and the yellow hint line. The texts are easy to read over the lava. No box covers a button. |  | Pass | Owner | 2026-10-28
C1.2 | C1 | Six texts have a dark box | F14a | F9_F14a_N62 | Both | 1280×720 | Same in ru at 1280×720 (the compact layout), then ja. | As C1.1: the boxes follow the texts to their compact positions and fit the longer ru / ja texts. |  | Pass | Owner | 2026-10-28
C1.3 | C1 | Six texts have a dark box | F14a | F9_F14a_N62 | Both | 1920×1080 | Watch the hint line until its hint disappears (about 2 s). | The hint's box disappears with the text. No empty dark box stays on screen. |  | Pass | Owner | 2026-10-28
C1.4 | Start the clone from PowerShell, so that it writes its own log: & 'C:\Program Files\Unity\Hub\Editor\6000.3.13f1\Editor\Unity.exe' -projectPath 'C:\Lesson\FallenStar-Spellcasters_clone_1' -logFile 'C:\Lesson\clone-editor.log' Last round the clone ran without it at least once: its lines went into the shared Editor.log and replaced the main Editor's, so I couldn't read the host side of A4. | Six texts have a dark box | F14a | F9_F14a_N62 | Both | 1920×1080 | While a hint is shown, switch the language (Read me → Switch language): en → ru → ja → en. | Each box resizes to its new text at once. Nothing stays the old size for more than a moment. | Yes | Pass | Owner | 2026-10-28
D. Send on the opponent's turn (N62). Two Editors.
D1.1 | D1 | The right hint for Send | N62 | F9_F14a_N62 | Client | 1920×1080 | During the HOST's Player action, press Send in the CLIENT window with nothing picked. | 'It's your opponent's turn.' (Last round it said 'Choose a target …'.) |  | Pass | Owner | 2026-10-28
D1.2 | D1 | The right hint for Send | N62 | F9_F14a_N62 | Host | 1920×1080 | During the CLIENT's Player action, press Send in the HOST window. | 'It's your opponent's turn.' |  | Pass | Owner | 2026-10-28
D1.3 | D1 | The right hint for Send | N62 | F9_F14a_N62 | Both | 1920×1080 | In your own Player action: press Send with no target confirmed; then pick a played card, click its target, Confirm, Send. | First 'Choose a target and press Confirm before Send.' Then the card is cast normally. |  | Pass | Owner | 2026-10-28
D1.4 | D1 | The right hint for Send | N62 | F9_F14a_N62 | Both | 1920×1080 | During the OPPONENT's Player action: pick your played card in the bottom row, click a target, press Confirm, then Send. When your own Player action starts, press Send again. | During their turn: 'It's your opponent's turn.' In your own turn the card is cast without picking it again (the package was kept). | Yes | Pass | Owner | 2026-10-28
E. Messages with the network off (repeat of last round's B, optional). One Editor is enough.
E1.1 | E1 | Failures show a message | F1 | N59_N61_F1 | Host | 1920×1080 | Log in and open the Lobby. Turn the PC's network off. Press Find Lobby and WAIT 15 s: the request needs about 10 s to give up. | 'Couldn't load the lobby list. Try again.' appears after about 10 s. Write in the notes how long it took. | Yes | Pass | Owner | 2026-10-28
E1.2 | E1 | Failures show a message | F1 | N59_N61_F1 | Host | 1920×1080 | Still offline: press Create Lobby and wait 15 s. | 'Couldn't create a lobby. Check your connection and try again.' You stay in the search view. | Yes | Pass | Owner | 2026-10-28
E1.3 | E1 | Failures show a message | F1 | N59_N61_F1 | Host | 1920×1080 | Stop Play Mode, start again (LoginScene), still offline, press Login anonymous and wait 15 s. Turn the network back on afterwards. | 'Couldn't sign in. Check your connection and try again.' You stay on the Login screen. | Yes | Pass | Owner | 2026-10-28
G. A new release build against an Editor.
G1.1 | G1 | Release build: mane, fade, boxes, clean log | N27, F9, F14a | All | Build | — | File → Build Profiles → Windows, Development Build OFF → Build to C:\Lesson\Spellcasters.Build (replace the old build). Start it. | The build succeeds and starts at the Login screen. |  | Pass | Owner | 2026-10-28
G1.2 | G1 | Release build: mane, fade, boxes, clean log | N27, F9, F14a | All | Build | — | Build = host, Editor = client. Play into the first Player action. | Both ponies have manes, the same colours in both windows. The big card fades; the HUD texts have their boxes. |  | Pass | Owner | 2026-10-28
G1.3 | G1 | Release build: mane, fade, boxes, clean log | N27, F9, F14a | All | Build | — | Close the build. Search its Player.log (Read me → Player build) for: Invalid mane material · Mane object is not assigned · Exception | None of them appears. |  | Pass | Owner | 2026-10-28
H. Both Editor logs, at the end.
H1.1 | H1 | Editor logs are clean | All | — | Both | — | Search the main Editor's log (%LOCALAPPDATA%\Unity\Editor\Editor.log) and C:\Lesson\clone-editor.log for 'Exception' and 'Invalid mane'. | No exception from game code, no mane warning. ('lobby not found' is known: N63. Write its time if you see it.) |  | Pass | Owner | 2026-10-28
H1.2 | H1 | Editor logs are clean | All | — | Both | — | Look for 'NetworkSceneManager.Dispose' (a NullReferenceException when you stop Play Mode, U9). | Write 'none', or which window and which scene you stopped in (e.g. 'clone, ResultScene'). | Yes | Pass | Owner | 2026-10-28

## Summary
Results summary
Calculated from the Checklist sheet; don't edit. Result: Fail if any row failed; Blocked if any row is blocked; Pass when every required row is Pass or N/A.
Group | Check | Covers | Task | Items | Required | Pass | Fail | Blocked | N/A | Not run / empty | Open (required) | Done % | Result
A1 | The mane sits on the head | N27 | N27 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | Pass
A2 | Two different colours, the same on both peers | N27 | N27 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 100% | Pass
A3 | A respawn keeps the colour | N27 | N27 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | Pass
A4 | A new match picks again | N27 | N27 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 100% | Pass
A5 | Selection still works | N27 | N27 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | Pass
B1 | Fade in and out | F9 | F9_F14a_N62 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 100% | Pass
B2 | The durations are editable | F9 | F9_F14a_N62 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | Pass
B3 | No fade after leaving | F9 | F9_F14a_N62 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | Pass
C1 | Six texts have a dark box | F14a | F9_F14a_N62 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 100% | Pass
D1 | The right hint for Send | N62 | F9_F14a_N62 | 4 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 100% | Pass
E1 | Failures show a message | F1 | N59_N61_F1 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 100% | Pass
G1 | Release build: mane, fade, boxes, clean log | N27, F9, F14a | All | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 100% | Pass
H1 | Editor logs are clean | All | — | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 100% | Pass
All | Overall |  |  | 28 | 20 | 28 | 0 | 0 | 0 | 0 | 0 | 100% | Pass

## Known issues
What you may see during the checks
Known and expected: don't mark a row Fail for these
You see | ID | Notes
The manes are white, black, brown, gold or pink. | N27 / Q1 | Expected this round. Your new palette (white, gold, pink, violet, orange; poll #15 Q1 = c) comes with the next task, TASK-N63_ManePalette.
The 'Confirm turn' button stays in English in ru and ja. | N64 | Known (found this round). Fixed by the next task, TASK-F15_F16_N64.
'LobbyServiceException: lobby not found' (red) right after a Disconnect. | N63 | Known (your A4.1 note). Harmless; the next task makes it quiet. Write the time if you see it.
A NullReferenceException in NetworkSceneManager.Dispose when you stop Play Mode. | U9 | Seen again last round (clone, after a match). Inside NGO; note it in H1.2, don't fail a row for it.
The dark box behind the announcer sits on the announcer's grey panel. | F14a | As specified. If you'd rather have no box there, write it in the notes of C1.1.
Many debug lines in the Editor Console (phases, 'Card clicked', 'DespawnBlock' …). | N34 | Expected in the Editor. Only release builds must be quiet (G1.3).
'No card selected for control package.' / 'Send ignored: …' warnings next to the hints. | — | Expected: the warnings stay, the hints are on screen.
'Remote client disconnected. Host continue' when the opponent leaves. | H6 | Expected: the forfeit path.
Offline, a failure message needs about 10 s to appear. | F1 | The online services give up after 10 s. Rows E1.x: wait 15 s.
With 10 cards the hand cards overlap a little; the right card takes the click. | UI3 | By design.
The lobby player item shows the short ID as the name and the full ID under it. | N29 | Parked by you.
MPLUSRounded1c-Medium SDF.asset shows as modified in git status after ru/ja text rendered. | N28 | Expected in the Editor. Restore it before committing (Read me → Before you commit).
Fixed in this round: mark the row Fail if you see these
You see | ID | Checked in
No mane on the pony; 'Invalid mane material index.' at every spawn. | N27 | A, G1.3, H1.1
The big card appears and disappears at once. | F9 | B
HP, Life and Mana hard to read over the lava. | F14a | C
Send on the opponent's turn says 'Choose a target and press Confirm before Send.' | N62 | D1
Found during the checks (add your own rows here)
What you saw | Row / when | Console text, screenshot